## 工作表1
Sprint ID | Task | Story Goal | Sub Task | Pages | Responsible | Estimated Hours Needed | Actual Hours Used | Dependency | Status
Implement the whole group & event related functions for SportsLover (10/27 - 11/7) Product Owner: Bin Zhu | Preperation Study | Good UI | Unified UI Decision for CSS & JS template and module | All | Bin Zhu | 2 | 2 | django-material, bootstrap | Success
|  | Clear Data | Data Model Decision for models.py | [5 empty] | Success
| Login Related Pages | Add sign out, sign in, password change, profile settings features in groups and personal pages; Create sign up page for initial information | Sign In Page | 1 | Bin Zhu | 3 | 3 | Remind user to sign in when request to create or join a group | Success
|  |  | Setting Page | 2 | Wenyan Hu |  |  |  | Success
|  |  | Password Change Page | 3 |  |  |  |  | Success
|  |  | Sign Up Page | 4 | Bin Zhu |  |  |  | Success
| Search Specific Group Feature on Main Page | Searching sports groups based on sports type, dates, expense | HTML Design | 5 | Wenyan Hu | 10 | 9 |  | Success
|  |  | Backend Search Fuction Support | [5 empty] | Success
| Groups Page | List all the groups information by the filter | HTML Design | 6 | Wenyan Hu | 10 | 11 |  | Success
|  |  | Backend Filter Fuction Support | [5 empty] | Success
| Personal Page | List user's profile, group event, groups & friend | HTML Design | 7 | Wenyan Hu | 10 | 8 |  | Success
|  |  | Backend Filter Fuction Support | [5 empty] | Success
| Group Create Form | Create a group for an event | Form Design | 6, 7 | Wenyan Hu | 10 | 12 |  | Success
|  |  | Backend Post Function Support | [5 empty] | Success
| Group Item Display | Get specific group information when clicking on groups page | Add logic to groups and personal view | 6, 7 | Wenyan Hu | 10 | 11 | Reuse the Group Create Form | Success
| Notifications | Notify any news or requests needed for user when he/she has logged in | HTML Design | All except main page | Wenyan Hu | 10 | 10 |  | Success
|  |  | Add logic in group request views for this | [5 empty] | Success
| Chat Room | Make every group chattable, and any two users can be friends | Implement group chatting for every group | All except main page | Bin Zhu | 10 | 15 |  | Success
|  |  | "Be-Friends" requests in one chat room |  | Wenyan Hu |  |  |  | Success
[5 empty] | Wenyan Hu |  |  |  | Success
|  |  | Add "Be-Friends" feature in Notification, and Personal Page | 7 | Wenyan Hu |  |  |  | Success
Add place-related functions and Map supporters for SportsLover (11/8 - 11/21) Product Owner: Wenyan Hu | Places Page | List all the sports places people have attended, including filter by rank, popularity, expense | HTML Design | 8 | Wenyan Hu | 4 | 5 |  | Success
|  |  | Backend Fuction Support | [5 empty] | Success
| Place Item Display | Get specific sports place information when clicking on places page | HTML Design | 9 | Wenyan Hu/Bin Zhu | 6 | 5 |  | Success
|  |  | Backend Fuction Support | [5 empty] | Success
| Comment and Rank | Add Comments and Ranks for the place you went | Notifications whenever the event ends | All except main page | Wenyan Hu | 6 | 5 | Remind user to rank and comment every time the group event ends | Success
|  |  | For each place item page, add comment and rank at the buttom, show average ranks and costs | 9 |  |  |  |  | Success
| Place Search on Main Page | Add search choice for places | Add search buttons for recent sports, nearby places, and most popular places | 5 | Wenyan Hu | 5 | 5 |  | Success
| Map Support on Main Page | Support place location search and map-based filter search feature | Embed google map search in the bottom of main search page | 5 | Bin Zhu | 6 | 8 | Google Maps API | Success
|  |  | Embed map with pins represents group events places for map-based search of groups |  | Bin Zhu | 6 | 7 |  | Success
Add payment function and check for security of the whole project(11/22 - 11/29) Product Owner: Wenyan Hu, Bin Zhu | Payment | Support individual payment for places to reserve or order | Implement payment function for every user | 9 | Bin Zhu | 20 | 20 | venmo api | Success
| Security Check | Check the security of the whole project for users and places | CSS, JavaScript related security check | None | Wenyan Hu | 6 | 6 |  | Success
|  |  | Network security written in the backend | None | Bin Zhu | 5 | 3 |  | Success
|  |  | Third-party API and plugin security | None | Wenyan Hu | 5 | 2 |  | Success
| Documents | Instructions for user usage | None | None | Wenyan Hu | 4 | 2 |  | Success
| Preparation For Demo | Deployment & Test | None | All | Wenyan Hu, Bin Zhu | 4 | 10 |  | Success
HTML Page: | 1.Sign In
2.Settings
3.Password Change
4.Sign Up
5.Main Page:search
6.Groups
7.Personal
8.Place
9.Place Individual